## table1
ITEM | APPROXIMATE COST** $
Bridge plug | 2500
3-1/2" OD Whipstock | 9675
Shear bolt | 100
Debris bearer | 300
Starter mill | 1147
2 Window mills | 2448
Watermellon mill | 1054
2-3/8" PH6 Tubing | 15081
Power tongs*** | 2000
Bit sub 2-3/8" reg box X 2-/3/8" PH6 box | 43
Saver sub 2-3/8" PH6 pin X 2-7/8" IF box | 176
Two safety valves 2-3/8" PH6 Box X pin | 800
Triplex pump*** | 5640
Power swivel | 8268
Safety clamp | 153
Slips and bowl 2-3/8" | 250
Slips 3-1/4" | 150
Slip type elevators | 260
Bits 3-7/8" with extra collar and gage protection | 23280
Directional drillers (survey equip., monel collars, down hole motors, subs) | 40000
Total $ | 113325
* Equipment in addition to that supplied by the drilling contractor
** Equipment rental costs including trucking, rental, inspection, and repair fees
*** This equipment may be supplied by the drilling contractor

## table3
MARING #3-B SRHW (ACTUAL COSTS) |  |  | STANDARD VERTICAL WELL (ESTIMATED COSTS)
WELL ACTIVITY | COMMENTS | COST $ | WELL ACTIVITY | COMMENTS | COST $
Survey and stake |  | NA | Survey and stake |  | 400
Drilling permit |  | 225 | Drilling permit |  | 850
Build roads & site |  | 300 | Build roads & site |  | 5000
Set bridge plug |  | 2450 | Set bridge plug |  | NA
Rig mobilization |  | 2000 | Rig mobilization |  | 3000
Footage rate - $12/ft. |  | NA | Footage rate - $12/ft. | 3000 ft. | 36000
Day rate - $4800 | 149.5 hrs. @ $200/hr. | 29900 | Day rate -$5400 |  | NA
Rig labor - $150/hr. | 35 2/3 hrs. - $1750 | 3600 | Rig labor - $225/hr. | 24 hrs. | 5400
Directional drilling |  | 75000 | Directional drilling |  | NA
Special equipment rental |  | 71700 | Special equipment rental |  | NA
Mud & pit liner |  | 350 | Mud & pit liner |  | 1000
Water & tank hauling |  | 1100 | Water & tank hauling |  | 2000
Surface casing |  | NA | Surface casing | 475 ft. @ $6.50/ft. | 3100
Cementing |  | NA | Cementing |  | 3500
Logging |  | NA | Logging |  | 6000
Supervision & consulting |  | 4000 | Supervision & consulting |  | NA
Reclamation |  | 250 | Reclamation |  | 2500
Production casing |  | NA | Production casing | 2800 ft. @ $3.00/ft. | 8400
Cementing |  | NA | Cementing |  | 6500
Perforating & bond log |  | NA | Perforating & bond log |  | 2000
Acid treatment |  | 3000 | Acid treatment |  | 4000
Completion rig |  | 2500 | Completion rig |  | 2500
Water disposal |  | NA | Water disposal |  | 1000
Trucking |  | 500 | Trucking |  | 500
Tubing | 2500 ft. @ $.75/ft. | 1875 | Tubing | 2500 ft. @ $.75/ft. | 1875
Casing & tubing head |  | 700 | Casing & tubing head |  | 700
Valves & connections |  | 500 | Valves & connections |  | 1000
Tank battery set up |  | 6900 | Tank battery set up |  | 7000
GPU separator w/ meter |  | 2300 | GPU separator w/ meter |  | 2300
Pumping unit w/ engine |  | 4500 | Pumping unit w/ engine |  | 4500
Rods & pump |  | 500 | Rods & pump |  | 2500
Flow line & sales line |  | 550 | Flow line & sales line |  | 2500
Labor |  | 1000 | Labor |  | 2500
Pipe line valves & fittings |  | 500 | Pipe line valves & fittings |  | 1000
| Total $ | 216200 |  | Total $ | 119525

## table4
SRHW FROM EXISTING WELL (ESTIMATED COSTS) |  |  | MRHW NEWLY DRILLED (ESTIMATED COSTS)
WELL ACTIVITY | COMMENTS | COST $ | WELL ACTIVITY | COMMENTS | COST $
Survey and stake |  | NA | Survey and stake |  | 400
Drilling permit |  | 225 | Drilling permit |  | 850
Build roads & site |  | 300 | Build roads & site |  | 5000
Set bridge plug |  | 2450 | Set bridge plug |  | NA
Rig mobilization |  | 2000 | Rig mobilization |  | 3000
Footage rate - $12/ft |  | NA | Footage rate - $12/ft | 2500 ft. | 30000
Day rate -$4800 | 5 days | 24000 | Day rate -$5400 | 4 days | 21600
Rig labor - $150/hr. | 35-2/3 hrs. | 3600 | Rig labor - $225/hr. | 24 hrs. | 5400
Directional drilling |  | 78000 | Directional drilling |  | 64000
Special equipment rental |  | 50000 | Special equipment rental |  | NA
Mud & pit liner |  | 350 | Mud & pit liner |  | 1000
Water & tank hauling |  | 1100 | Water & tank hauling |  | 2000
Surface casing |  | NA | Surface casing | 475 ft. @ $6.50/ft. | 3100
Cementing |  | NA | Cementing |  | 3500
Logging |  | NA | Logging |  | 4000
Supervision & Consulting |  | 4000 | Supervision & Consulting |  | 5000
Reclamation |  | 250 | Reclamation |  | 2500
Production casing |  | NA | Production casing | 3000 ft. @ $3.00/ft. | 9000
Cementing |  | NA | Cementing |  | 6000
Perforating & bond log |  | NA | Perforating & bond log |  | NA
Acid treatment |  | 3000 | Acid treatment |  | 4000
Completion rig |  | 2500 | Completion rig |  | 2500
Water disposal |  | NA | Water disposal |  | 1000
Trucking |  | 500 | Trucking |  | 500
Tubing | 2500 ft. @ $0.75/ft. | 1875 | Tubing | 3000 ft. @ $.75/ft. | 2250
Casing & tubing head |  | 700 | Casing & tubing head |  | 700
Valves & connections |  | 500 | Valves & connections |  | 1000
Tank battery set up |  | 6900 | Tank battery set up |  | 7000
GPU separator w/ meter |  | 2300 | GPU separator w/ meter |  | 2300
Pumping unit w/ engine |  | 4500 | Pumping unit w/ engine |  | 4500
Rods & pump |  | 500 | Rods & pump |  | 2500
Flow line & sales line |  | 550 | Flow line & sales line |  | 2500
Labor |  | 1000 | Labor |  | 2500
Pipe line valves & fittings |  | 500 | Pipe line valves & fittings |  | 1000
| Total $ | 191600 |  | Total $ | 200600