## Sheet16
GENERAL TASK | DATE & TIME (AUGUST 1998) | TOTAL HRS. | DETAIL OF LABOR
Log and Set Bridge Plug | Fri. 14th 10:30 AM - Fri. 14th 1:30 PM | 3.0 hrs. | Rig up - 1.0 hrs., Log - .5 hrs., Set bridge plug - .5 hrs., Rig down
1.0 hrs.
Build Location and Move in Equipment | Fri. 14th 12:00 PM - Sun. 23rd 2:00 PM
Gyro Survey and Preparation | Sun. 23rd 2:00 PM - Sun. 23rd 8:30 PM | 6.5 hrs. | Rig up - 5.0 hrs., Survey - 1.5 hrs.
Wiper Run | Sun. 23rd 8:30 PM - Mon. 24th 8:00 AM | 11.5 hrs. | Rig up - 1 hrs., Trip - 8.5 hrs., Circulate - 1.0 hrs., Rig down - 1.0
hrs.
Set Whipstock and Mill Starter Hole | Mon. 24th 8:00 AM - Tues. 25th 1:30 AM | 17.5 hrs. | Rig up - 5.0 hrs., Trip - 8.0 hrs.,Set whipstock - .5 hrs., Test and
repair BOP - 1.0 hrs., Mill - 1.5 hrs. (ave. rate - 30.0 min./ft.),
Circulate - .5 hrs., Rig down - 1.0 hrs.
Mill Window and Ream | Tues. 25th 1:30 AM - Tues. 25th 9:15 PM | 19.75 hrs. | Rig up - 1.75 hrs., Trip - 9.25 hrs., Mill - 4.75 hrs. (ave. rate - 31.0
min./ft.), Ream - 1.0 hrs., Circulate 1.25 hrs., Rig down - 1.75 hrs.
Drill Straight Hole to Kick Off Point | Tues. 25th 9:15 PM - Wed. 26th 6:00 AM | 8.75 hrs. | Rig up - 1.75 hrs., Trip - 4.0 hrs., Drill - 1.75 hrs. (ave. rate - 3.0
min./ft.), Rig down - 1.25 hrs.
Drill First Part of Curve | Wed. 26th 6:00 AM - Thur. 27th 4:30 AM | 22.5 hrs. | Rig up 4.75 hrs., Trip - 5.0 hrs., Drill - 10.75 hrs. (ave. rate - 8.0
min./ft.), Circulate - .25 hrs., Rig down - 1.75 hrs.
Dropped Pipe and Fish | Thur. 27th 4:30 AM - Thur. 27th 12:30 PM | 8.0 hrs. | Rig up - 2.25 hrs., Trip 4.5 hrs., Fish - .25 hrs., Rig down - 1.0 hrs.
Drill Second Part of Curve | Thur. 27th 12:30 PM - Fri. 28th 3:45 AM | 15.25 hrs. | Rig up - 1.5 hrs., Trip - 4.0 hrs., Ream - 2.25 hrs., Drill - 5.5 hrs.
(ave. rate - 3.5 min./ft.), Circulate - 1.0 hrs., Rig down - 1.0 hrs.
Drill First Horizontal Leg | Fri. 28th 3:45 AM - Fri. 28th 9:00 PM | 17.25 hrs. | Rig up - 1.0 hrs., Trip 4.5 hrs., Ream - 2.0 hrs., Drill - 8.5 hrs.
(ave. rate - 5.0 min./ft.), Circulate - .25 hrs., Rig down - 1.0 hrs.
Drill Second Horizontal Leg | Fri. 28th 9:00 PM - Sat. 29th 1:00 PM | 16.0 hrs. | Rig up - .5 hrs., Trip 4.5 hrs., Drill - 7.25 hrs. (ave. rate - 3.0
min./ft.), Circulate - 1.0 hrs., Rig down - 2.75 hrs.
Well Treatment | Sat. 29th 1:00 PM - Sat. 29th 6:00 PM | 5.0 hrs. | Rig up - 1.25 hrs., Trip - 3.25 hrs., Acidize - .5 hrs.
Total | Fri. 14th 2:00 PM - Sat. 29th 6:00 PM | 151.0 hrs. | Rig up - 26.75 hrs., Log - .5 hrs., Set bridge plug - .5 hrs.,
Survey - 1.5 hrs., Trip - 55.5 hrs., Set whipstock - .5 hrs., Mill -
6.25 hrs., Drill - 31.25 hrs., Ream - 5.25 hrs., Test and repair BOP -
1.0 hrs., Circulate - 5.25 hrs., Fish - .25 hrs., Acidize - .5 hrs.,
Rig down - 13.5 hrs.